## Slide 1: Volunteers’ Management System
Apollo Group
IT University of Gothenburg

## Slide 2: Apollo Group
Abdollah Tabareh
Gilana Ramezani
Abdullah Arslan
Waseem Soomro
Shobha B C
Mustafa Al-Zubaidi
Tigran Harutyunyan

## Slide 3: Agenda
Background
Initial Estimation
Baseline Schedule
Project Status
Future Plans
Problems
Defect Tracking System
VMS in action
Q&A

## Slide 4: Background
Volunteer Management System
Request the citizens for the help
Allow citizens to help with their stuff
Allow crisis manager to organize citizens
Allow to resolve the crisis with the help of the citizens
The users are crisis managers and citizens

## Slide 5: Overall perspective
VMS

## Slide 6: Chart
Chart: 
| Management - 275 (10%) | Prj. Initiation - 30 (1%) | Req. Refinement - 25 (1%) | A&D - 200 (7%) | Implement - 1350 (48%) | Test - 500 (18%) | Training - 420 (15%)
Effort | 275 | 30 | 25 | 200 | 1350 | 500 | 420

## Slide 7: Baseline Schedule

## Slide 8: Status of Deliverables
Due date: 28 April 2010
Planed | Status
Project management plan | Completed
QA plan | Completed
SAD and SDD | Completed
65% of functionality developed | 61% is completed
65% of functionality tested | ???
100% of test cases ??? | ???
1st draft of the User guideline | In progress

## Slide 9: Development progress
Chart: 
| I 1 | I 2 | I 3 | I 4 | I 5 | I 6 | I 7 | I 8
Scheduled | 0 | 0 | 0 | 20 | 30 | 50 | 65 | 100
Actual | 0 | 0 | 0 | 0 | 10 | 25 | 61
%
Iterations

## Slide 10: Status Summary
Schedule performance indicators:
  SPI < 60%
  60 %<= SPI < 85%
  SPI >= 85%
  Project’s schedule indicator till Monday 26 of April shows:
87%

## Slide 11: Future Plans
9 May: Beta release, part of user supporting materials
19 May: Final release, all of user supporting materials
And quality and managerial reports for all iterations

## Slide 12: Problems
Unavailability of Rational tools
J2ME and mobile technologies problems
  Detecting the location from the mobile device
  Capturing a video and photo from the mobile device

## Slide 13: Defect Tracking System
http://trac6.assembla.com/apollogroup/report

## Slide 14: VMS in action
VMS Portal
http://licrp.dnsalias.net/apollo/Incident.aspx?Action=Create
Mobile application

## Slide 15: Questions