## UC
UC | Simple | average | complex | Weight | Percent
Create Crisis |  | 1 |  | 10 | 3.704% | done | 1 | 0.037037 |  | OK
Edit Crisis |  | 1 |  | 10 | 3.704% | done | 1 | 0.037037 |  | OK
Close Crisis | 1 |  |  | 5 | 1.852% |  | 1 | 0.018519 |  | OK
Create Incident |  | 1 |  | 10 | 3.704% | done | 1 | 0.037037 |  | OK
Edit Incident |  | 1 |  | 10 | 3.704% |  | 1 | 0.037037 |  | OK | Cancel button is missing | Incident box should be better
Create Request |  | 1 |  | 10 | 3.704% |  | 1 | 0.037037 |  | OK
Edit Request |  | 1 |  | 10 | 3.704% |  |  | 0 |  | OK | Canceling should be analyzed
Answer Request |  | 1 |  | 10 | 3.704% |  | 1 | 0.037037 |  | OK
Manager login | 1 |  |  | 5 | 1.852% | done | 1 | 0.018519 |  | OK | Check it and correct style
Volunteer Login by mobile | 1 |  |  | 5 | 1.852% |  | 1 | 0.018519 |  | OK
Manager Registration | 1 |  |  | 5 | 1.852% | done | 1 | 0.018519 |  | OK | field checking
Volunteer Registration | 1 |  |  | 5 | 1.852% | done | 1 | 0.018519 |  | OK
Volunteer Edits profile | 1 |  |  | 5 | 1.852% | done | 1 | 0.018519 |  | OK | Be sure vlunteer or manager updates it
Create Statistical Report | 1 |  |  | 5 | 1.852% |  |  | 0
Report Incident |  |  | 1 | 15 | 5.556% |  | 1 | 0.055556 |  |  | Web method is not ready. Tigran will prepare signature
Send Alert |  | 1 |  | 10 | 3.704% |  | 1 | 0.037037 | 1 |  | Search functionality should be added
Report Incident Progress |  |  | 1 | 15 | 5.556% |  | 1 | 0.055556 |  |  | Web method is not ready. Tigran will prepare signature
Search Volunteers | 1 |  |  | 5 | 1.852% |  |  | 0 |  | Canceled
View Volunteers’ Incident Report |  | 1 |  | 10 | 3.704% |  | 1 | 0.037037 | 1 |  | Mohsen: will be done
View Incident Information | 1 |  |  | 5 | 1.852% |  | 1 | 0.018519 |  | Canceled
Close Incident | 1 |  |  | 5 | 1.852% |  | 1 | 0.018519 |  | OK | Add prompt
Volunteer Profile Login | 1 |  |  | 5 | 1.852% | done | 1 | 0.018519 |  | OK | Overview
Get Alert | 1 |  |  | 5 | 1.852% |  | 1 | 0.018519 |  | OK
View Crisis | 1 |  |  | 5 | 1.852% |  | 1 | 0.018519 |  | Canceled
Manager Profile approval |  | 1 |  | 10 | 3.704% |  | 1 | 0.037037 |  |  | ASK Mohsen | Mohsen: Yes it's done in manreg.aspx
Define Region on the map |  | 1 |  | 10 | 3.704% |  | 1 | 0.037037 |  | OK
Remove Request |  | 1 |  | 10 | 3.704% |  | 1 | 0.037037 | 1 | Suspend request
Manage Manager Profile | 1 |  |  | 5 | 1.852% | done | 1 | 0.018519 |  | OK | Check it and correct style
Delete Volunteer Profile | 1 |  |  | 5 | 1.852% |  | 1 | 0.018519 |  | OK
Crisis Information Report | 1 |  |  | 5 | 1.852% |  |  | 0 |  | left for now
Progress Report | 1 |  |  | 5 | 1.852% |  |  | 0 |  | left for now
Resource Utilization report | 1 |  |  | 5 | 1.852% |  |  | 0 |  | left for now
Save Report | 1 |  |  | 5 | 1.852% |  |  | 0 |  | left for now
Create Backup | 1 |  |  | 5 | 1.852% |  |  | 0 |  | left for now
View Volunteer Incident Progress report |  | 1 |  | 10 | 3.704% |  | 1 | 0.037037 |  | OK
Restore from backup |  | 1 |  | 10 | 3.704% |  |  | 0 |  | left for now
UUCW | 100 | 140 | 30 | 270 | 100% |  | 27 | 0.7963

## Actors
Category | Actors | Act No. | Weight | UAW | uupc
Simple | GIS system | 1 | 1 | 1
Complex | Volunteer Manager | 2 | 3 | 6
|  |  |  | 7 | 277

## Sheet3
UC
Create Crisis | OK
Edit Crisis | OK
Close Crisis | OK
Create Incident | OK
Edit Incident | OK | Cancel button is missing | Incident box should be better
Create Request | OK | Workon style
Edit Request | OK | Canceling should be analyzed | Change title
Answer Request | OK
Manager login | OK | Check it and correct style
Volunteer Login by mobile | OK
Manager Registration | OK | field checking
Volunteer Registration | OK
Volunteer Edits profile | OK | Be sure vlunteer or manager updates it
Create Statistical Report
Report Incident |  | Web method is not ready. Tigran will prepare signature
Send Alert |  | Search functionality should be added
Report Incident Progress |  | Web method is not ready. Tigran will prepare signature
Search Volunteers | Canceled
View Volunteers’ Incident Report
View Incident Information | Canceled
Close Incident | OK | Add prompt
Volunteer Profile Login | OK | Overview
Get Alert | OK
View Crisis | Canceled
Manager Profile approval |  | ASK Mohsen
Define Region on the map | OK
Remove Request | Suspend request
Manage Manager Profile | OK | Check it and correct style
Delete Volunteer Profile | OK
Crisis Information Report | left for now
Progress Report | left for now
Resource Utilization report | left for now
Save Report | left for now
Create Backup | left for now
View Volunteer Incident Progress report | OK
Restore from backup | left for now
UUCW