## Sheet1
UC | Simple | average | complex | Weight | Percent
Create Crisis |  | 1 |  | 10 | 4% | 1 | 10
Edit Crisis |  | 1 |  | 10 | 4% | 1 | 10
Close Crisis | 1 |  |  | 5 | 2% | 1 | 5
Create Incident |  | 1 |  | 10 | 4% | 1 | 10
Edit Incident |  | 1 |  | 10 | 4% | 1 | 10
Create Request |  | 1 |  | 10 | 4% | 1 | 10
Edit Request |  | 1 |  | 10 | 4% | 1 | 10
Answer Request |  | 1 |  | 10 | 4% | 1 | 10
Manager login | 1 |  |  | 5 | 2% | 1 | 5
Volunteer Login by mobile | 1 |  |  | 5 | 2% | 1 | 5
Manager Registration | 1 |  |  | 5 | 2% | 1 | 5
Volunteer Registration | 1 |  |  | 5 | 2% | 1 | 5
Volunteer Edits profile | 1 |  |  | 5 | 2% | 1 | 5
Create Statistical Report | 1 |  |  | 5 | 2% |  | 0
Report Incident |  |  | 1 | 15 | 6% | 1 | 15
Send Alert |  | 1 |  | 10 | 4% | 1 | 10
Report Incident Progress |  |  | 1 | 15 | 6% | 1 | 15
Search Volunteers | 1 |  |  | 5 | 2% | 1 | 5
View Volunteers’ Incident Report |  | 1 |  | 10 | 4% | 1 | 10
Close Incident | 1 |  |  | 5 | 2% | 1 | 5
Volunteer Profile Login | 1 |  |  | 5 | 2% | 1 | 5
Get Alert | 1 |  |  | 5 | 2% | 1 | 5
Manager Profile approval |  | 1 |  | 10 | 4% | 1 | 10
Define Region on the map |  | 1 |  | 10 | 4% | 1 | 10
Manage Manager Profile | 1 |  |  | 5 | 2% | 1 | 5
Delete Volunteer Profile | 1 |  |  | 5 | 2% | 1 | 5
Crisis Information Report | 1 |  |  | 5 | 2% |  | 0
Progress Report | 1 |  |  | 5 | 2% |  | 0
Resource Utilization report | 1 |  |  | 5 | 2% |  | 0
Save Report | 1 |  |  | 5 | 2% |  | 0
Create Backup | 1 |  |  | 5 | 2% |  | 0
View Volunteer Incident Progress report |  | 1 |  | 10 | 4% | 1 | 10
Restore from backup |  | 1 |  | 10 | 4% |  | 0
UUCW | 90 | 130 | 30 | 250 | 100% | 26 | 210 | 0.84