## Slide 1: Volunteers’ Management System
Apollo Group
IT University of Gothenburg

## Slide 2: Apollo Group
Abdollah Tabareh
Gilana Ramezani
Abdullah Arslan
Waseem Soomro
Shobha B C
Mustafa Al-Zubaidi
Tigran Harutyunyan

## Slide 3: Agenda
Background
Initial Estimation
Baseline Schedule
Project Status
Future Plans
Defect tracking system
VMS in action
Q&A

## Slide 4: Background
Volunteer Management System
Request the citizens for the help
Allow citizens to help with their stuff
Allow crisis manager to organize citizens
Allow to resolve the crisis with the help of the citizens
The users are crisis managers and citizens

## Slide 5: Overall perspective
VMS

## Slide 6: Chart
Chart: 
| Management - 275 | Prj. Initiation - 30 | Req. Refinement - 25 | A&D - 200 | Implement - 1350 | Test - 500 | Training - 420
Effort | 275 | 30 | 25 | 200 | 1350 | 500 | 420

## Slide 7: Baseline Schedule

## Slide 8: Status of deliverables
End date: 28 April 2010
Project management plan
QA plan
SAD and SDD
65% developed functionality - 61 % is completed
65% of tested functionality – xx % is completed
100% of test cases - completed
1st draft of the User guideline – in progress

## Slide 9: Development progress
Chart: 
| I 1 | I 2 | I 3 | I 4 | I 5 | I 6 | I 7 | I 8
Scheduled | 0 | 0 | 0 | 20 | 30 | 50 | 65 | 100
Actual | 0 | 0 | 0 | 0 | 10 | 25 | 61 | 61

## Slide 10: Status Summary
Schedule indicators:
  SPI < 60%
  60 %<= SPI < 85%
  SPI >= 85%
  So the project schedule indicator till Monday 26 of April shows:
87%

## Slide 11: Future Plans
28 April: 65% of fully tested functionality, 100% of test cases
9 May: Beta release, part of user supporting materials
19 May: Final release, all of user supporting materials
And quality and managerial reports for all iterations

## Slide 12: Defect tracking system
http://trac6.assembla.com/apollogroup/report

## Slide 13: VMS in action
VMS Portal
http://licrp.dnsalias.net/apollo/Incident.aspx?Action=Create
Mobile application

## Slide 14: Questions