## UC
UC | Simple | average | complex | Weight | Percent
Create Crisis |  | 1 |  | 10 | 3.704% | done | 1 | 0.037037 |  | OK
Edit Crisis |  | 1 |  | 10 | 3.704% | done | 1 | 0.037037 |  | OK
Close Crisis | 1 |  |  | 5 | 1.852% |  | 1 | 0.018519 |  | OK
Create Incident |  | 1 |  | 10 | 3.704% | done | 1 | 0.037037 |  | OK
Edit Incident |  | 1 |  | 10 | 3.704% |  | 1 | 0.037037 |  | OK
Create Request |  | 1 |  | 10 | 3.704% |  | 1 | 0.037037 |  | OK
Edit Request |  | 1 |  | 10 | 3.704% |  |  | 0 |  | OK | Canceling should be analyzed
Answer Request |  | 1 |  | 10 | 3.704% |  | 1 | 0.037037 |  | OK
Manager login | 1 |  |  | 5 | 1.852% | done | 1 | 0.018519 |  | OK | Check it and correct style
Volunteer Login by mobile | 1 |  |  | 5 | 1.852% |  | 1 | 0.018519 |  | OK
Manager Registration | 1 |  |  | 5 | 1.852% | done | 1 | 0.018519 |  | OK | field checking
Volunteer Registration | 1 |  |  | 5 | 1.852% | done | 1 | 0.018519 |  | OK
Volunteer Edits profile | 1 |  |  | 5 | 1.852% | done | 1 | 0.018519 |  | OK | Be sure vlunteer or manager updates it
Create Statistical Report | 1 |  |  | 5 | 1.852% |  |  | 0
Report Incident |  |  | 1 | 15 | 5.556% |  | 1 | 0.055556
Send Alert |  | 1 |  | 10 | 3.704% |  | 1 | 0.037037 | 1 |  | Search functionality should be added
Report Incident Progress |  |  | 1 | 15 | 5.556% |  | 1 | 0.055556
Search Volunteers | 1 |  |  | 5 | 1.852% |  |  | 0 |  | Canceled
View Volunteers’ Incident Report |  | 1 |  | 10 | 3.704% |  | 1 | 0.037037 | 1
View Incident Information | 1 |  |  | 5 | 1.852% |  | 1 | 0.018519 |  | Canceled
Close Incident | 1 |  |  | 5 | 1.852% |  | 1 | 0.018519 |  | OK | Add prompt
Volunteer Profile Login | 1 |  |  | 5 | 1.852% | done | 1 | 0.018519 |  | OK | Overview
Get Alert | 1 |  |  | 5 | 1.852% |  | 1 | 0.018519 |  | OK
View Crisis | 1 |  |  | 5 | 1.852% |  | 1 | 0.018519 |  | Canceled
Manager Profile approval |  | 1 |  | 10 | 3.704% |  | 1 | 0.037037 |  |  | ASK Mohsen
Define Region on the map |  | 1 |  | 10 | 3.704% |  | 1 | 0.037037 |  | OK
Remove Request |  | 1 |  | 10 | 3.704% |  | 1 | 0.037037 | 1 | Suspend request
Manage Manager Profile | 1 |  |  | 5 | 1.852% | done | 1 | 0.018519 |  | OK | Check it and correct style
Delete Volunteer Profile | 1 |  |  | 5 | 1.852% |  | 1 | 0.018519 |  | OK
Crisis Information Report | 1 |  |  | 5 | 1.852% |  |  | 0 |  | left for now
Progress Report | 1 |  |  | 5 | 1.852% |  |  | 0 |  | left for now
Resource Utilization report | 1 |  |  | 5 | 1.852% |  |  | 0 |  | left for now
Save Report | 1 |  |  | 5 | 1.852% |  |  | 0 |  | left for now
Create Backup | 1 |  |  | 5 | 1.852% |  |  | 0 |  | left for now
View Volunteer Incident Progress report |  | 1 |  | 10 | 3.704% |  | 1 | 0.037037 |  | OK
Restore from backup |  | 1 |  | 10 | 3.704% |  |  | 0 |  | left for now
UUCW | 100 | 140 | 30 | 270 | 100% |  | 27 | 0.7963

## Actors
Category | Actors | Act No. | Weight | UAW | uupc
Simple | GIS system | 1 | 1 | 1
Complex | Volunteer Manager | 2 | 3 | 6
|  |  |  | 7 | 277

## Sheet3
- web service methods: few service methods are remaining. Tigran will send what does he need.
- Automatic requesting procedure should be updated. It doesnt update incident need list. It only updates request need list. I will do it.
- Logging feature is added but only few methods are using it. We should add logging statements in codes.
- Security checking (authentication and authorization) must be added to page base or master page
- In send alert page, manager should search the volunteers to send that alert.
- list of alerts and view new incident reports pages must be done.
- I have changed sitemap structure. It was misleading. We can talk it later. It is now a bulleted list that is used like a menu. All pages must fill that menu individually. I added that code to pages that i implemented. Other pages remain.
- All of the buttons in the web site should have same style.
- We should have a common style for links, form values, testboxes and etc. Currently different pages have different style.
- The default page of the site should contain a system description and also a login form at one side.
- Manager profile approval??? we dont know it. Is it finished? Who and how approves ?
- There are also some issues related to finished pages. Check the Estimation.xlsx file. The K column contains status. and right side of K contains issues.
UUCW